## Rebecca Hodges
Name: | Rebecca Hodges | Project Group (Name/Number): |  | Group 1
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Initital team meeting - Discuss ideas and members strengths & experience | 1 hour | Yes
2 | 2023-05-07 | Team meeting - Gave ideas for API's | 1 hour | Yes
2 | 2023-05-08 | Drafted project ideas and what features it could have (suggesting plants based on user's requirements) | 30 mins | Yes
2 | 2023-05-10 | Homework 2 work | 1 hour | Yes
2 | 2023-05-10 | Team meeting to finalise project ideas and divide submission sections | 1 hour 10 mins | Yes
3 | 2023-05-12 | Homework 2 work and submission | 1 hour | Yes
4 | 2023-05-15 | Team meeting | 50 mins | Yes
4 | 2023-05-15 | Created python files and made comments outlining code | 2.5 hours | Yes
4 | 2023-05-16 | Created classes for plants | 1.5 hour | Yes
4 | 2023-05-17 | Team meeting | 30 mins | Yes
4 | 2023-05-21 | Changed classes and created calendar functions | 3 hours | No
5 | 2023-05-22 | Team meeting | 35 mins | Yes
5 | 2023-05-22 | Connected calendar to database and successfully connected to run with calendar | 2 hours | Yes
5 | 2023-05-24 | Team meeting | 45 mins | Yes
5 | 2023-05-24 | Worked on unit testing all functions, general running order and adjusting algorithms for calculating days. After meeting decided to refactor to include more OOP principles for plants and watering calendar. | 6 hours | No | Will need to redo unit tests due to refactor
5 | 2023-05-25 | More testing, added the ability to display treatment advice if user reported diseases. Also added a summary. | 2.5 hours | No | Diseases function currently not syncing
5 | 2023-05-26 | Fixed bug with database and completed calendar feature and testing. Fixed disease function not displaying correctly. | 5 hours | No
5 | 2023-05-16 | Discussion regarding DB integration issue | 30 mins | Yes
5 | 2023-05-26 | Team meeting - Submited code to compile and discussed how to formulate report. | 2.5 hours | Yes
5 | 2023-05-27 | Report Writing - Drafted sections tasked to work on. | 45 mins | No
5 | 2023-05-28 | Report Writing - Wrote challenges and agile development section in addition to calendar overview. Collaborated with team on Slack to produce final report. | 2 hours | Yes
5 | 2023-05-28 | Compiled team logbooks | 20 mins | Yes

## Oluwaferanmi Olatunji
Name: Oluwaferanmi Olatunji |  | Project Group (Name/Number): Team 1
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed?
| 2023-04-27 | Team meeting to discuss skill of each team member, what we can achieve | 1hr | yes
2 | 2023-05-07 | Discussion and deliberation of ideas from team members | 1 hr | Yes
2 | 2023-05-10 | Meeting to finalize project Ideas and discuss team member roles | 1 hr | Yes
3 | 2023-05-12 | Team meeting with Jia and Emina to discuss completion of project plan homework 2 and next meeting arrangment. | 20 mins | Yes
3 | 2023-05-13 | Meeting with Jia and Rinsola to discuss role distribution and API research. Agreed to work alongside Rinsola to structure PlantPal's My Plants database feature | 30 mins | Yes
4 | 2023-05-15 | Research on Columns necessary for the user, plant and plant details column in the database | 3hrs | yes
4 | 2023-05-16 | Designed Frontend for plantpal, Clone repo and set it up for PlantPal locally | 5hrs | yes
4 | 2023-05-17 | Continue Designing Frontend for plantpal. Assisted Emina in conflicts and setting up .env | 7hr+ | yes
4 | 2023-05-18 | Implemented frontend for Plantpal | 7hr+ | yes
4 | 2023-05-19 | Set up PlantPal database, sql files for table creation and mock data for insertions for the purpose of testing. Had 2hr meeting with Emina to discuss backend structure, and the structure of the sql table 'PlantDetails' so that my functions in python-sql-connector corresponded to the table columns and data and could be inserted/removed correctly. | 2hr30 | yes
5 | 2023-05-22 | Walkthrough of backend logic in relation with application flow | 3hr | yes
5 | 2023-05-23 | More research on app's flow before commencing implementation | 2hr30 | yes
5 | 2023-05-24 | Wrote functions to generate a unique id, get users, get user by id, add user to the database | 1hr50 | yes
5 | 2023-05-25 | Wrote functions to login, verify password, hash password, check if a user already exist in the db for the user module | 5hr30 | yes
5 | 2023-05-26 | wrote functions to define end points for login, register, get a user by id and to get all users. | 4hr | yes
5 | 2023-05-27 | Wrote unit tests for the user class, db connection worked with ying in restructuring application | 3hrs | yes
5 | 2023-05-28 | Worked on ReadMe along sides Ying, cleaned up project, Wrapped up project report with other team members, included Technical and Non technical Features, Frameworks, Background. | 4hrs | yes

## Ying-Ting Liu
Name: | Ying-Ting Liu | Project Group (Name/Number): Group1
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Initial Meeting | 1 Hour | Yes
2 | 2023-05-07 | Meeting 2 | 1 Hour | Yes
3 | 2023-05-10 | Homework 2 | 1 Hour | No
3 | 2023-05-10 | Reading Group Minutes, and discuss task | 1 Hour | Yes
3 | 2023-05-11 | Homework 2 | 1 Hour | No
3 | 2023-05-12 | Finalize Homework 2 | 1 Hour | Yes
4 | 2023-05-16 | Research how to do it | 1 Hour | No
4 | 2023-05-17 | Meeting 5 | 1 Hour | Yes
4 | 2023-05-18 | Setting up environment and Code | 1 Hour | No
4 | 2023-05-20 | Code | 2 Hour | No
4 | 2023-05-21 | Code | 2 Hour | No
5 | 2023-05-23 | Code | 2 Hour | No
5 | 2023-05-26 | Finalize my function | 4 Hour | No
5 | 2023-05-26 | Meeting 8 | 2.5 Hour | Yes
5 | 2023-05-27 | Merge Project | 3 Hour | No
5 | 2023-05-27 | Fix bugs and discussion | 2 Hour | No
5 | 2023-05-27 | Final Report | 1.5 Hour | No
5 | 2023-05-27 | Log Report | 1 Hour | No
5 | 2023-05-28 | Fix bugs and discussion | 2 Hour | Yes
5 | 2023-05-28 | Log Report | 0.5 Hour | Yes
5 | 2023-05-27 | Final Report | 1 Hour | Yes

## Emina Ergul
Name: Emina Ergul |  | Project Group (Name/Number): Team 1
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
| 2023-04-27 | Initial team meeting introductions, and to discuss interests, strengths, weaknesses | 1hr | yes
2 | 2023-05-07 | Team meeting to discuss potential project ideas(suggested music app, space data app), discuss team roles, preferences, time management, and regular meeting schedule. | 1 hr | Yes
2 | 2023-05-10 | Team meeting to finalise project idea(Plant care app) and organise week 3 project homework roles, discuss main features of our application and our limits/preferences. Sugessted I would like to work on Database integration and that we should start by finding a relevant API. | 1 hr | Yes
3 | 2023-05-12 | Team meeting with Jia and Rinsola to discuss completion of project plan homework 2 and next meeting arrangment. Finished creating program architecture diagram for homework. | 20 mins | Yes
3 | 2023-05-13 | Meeting with Jia and Rinsola to discuss role distribution and API research. Agreed to work alongside Rinsola to structure PlantPal's My Plants database feature | 30 mins | Yes
4 | 2023-05-15 | Team meeting to confirm my suggested choice of API and confirm feature distrubution for each team member. Wrote initial code in my_plants_main.py to connect to RapidAPI house plant API and return data based on user input. Encountered github authorisation issue and was unable to push code | 1hr | yes
4 | 2023-05-16 | Fixed github authorisation issue by changing team repo permissions. Pushed code for team to understand the API data available | 30mins | yes
4 | 2023-05-17 | Team meeting for progress review. Fixed merge conflict involving .gitignore and .env file problems with Rinsola, in order to hide API key and details | 1hr | yes
4 | 2023-05-18 | Started python-sql-connector.py by writing basic functions to add/remove/display data from the PlantPal database 'PlantDetails' column to act as users 'My Plants' collection | 1hr30 | yes
4 | 19//05/23 | Had 2hr meeting with Rinsola to discuss backend structure, and the structure of the sql table 'PlantDetails' so that my functions in python-sql-connector corresponded to the table columns and data and could be inserted/removed correctly. | 2hr30 | yes
5 | 2023-05-22 | Team meeting for progress updates, to decide against creating a frontend, confirm I will add user input plant disease feature. Debugged add_plant function by adjusting data types inserted into sql table plantDetails. Refactored my_plants_main.py by creating more structure through functions. Started user_input_disease in my_plants_main.py | 3hr | yes
5 | 2023-05-23 | Complete functions to remove, and display data from the PlantDetails sql table. Also wrote function in my_plants_main.py that takes optional user input for plant disease if their searched for plant includes disease data from the API. Spoke with Rinsola to sync the PlantDetails table for this addition with my add_plant query function in python. | 2hr30 | yes
5 | 2023-05-24 | Team meeting for progress update, said I will work on extra parts of final report(like intro/conclusion/diagrams) as well as sections about our own features. Started writing unit tests for my_plants_main.py | 1hr50 | yes
5 | 2023-05-25 | Meeting with Rinsola to discuss further SQL PlantDetails table changes to include all the relevant data we need. Faced multiple error messages after making changes and had to debug multiple functions in my_plants_main.py and python-sql-connector. Rewrote add_plant query in python-sql-connector.py to align with sql table. Refatored my_plants_main.py into further functions and try/except blocks to create a better prgram flow initialised with search_plant(). | 5hr30 | yes
5 | 2023-05-26 | Complete some unit tests, but struggled to implement tests for some functions in my_plants_main.py(such as remove_from_my_plants) which depend on a flow of continuous user input that I failed to mock. Team meeting to push all code to github, check for errors and functionality, discuss roles for writing final report. | 4hr | yes
5 | 2023-05-27 | Wrote introduction for final report and planning/started writing the rest of my parts. Made some final changes to my imports after Rinsola and Ying Ting edited folder structure and file names. | 3hrs | yes
| 2023-05-28 | Wrote conclusion, and created program architecture diagram for final report. Communicated a lot with team about finalisations before submission | 4hrs | yes
Total time: 33hr10

## Jia Chi Leow
Name: Jia Chi Leow |  | Project Group (Name/Number): Group 1
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Group had the 1st meeting on Zoom at 19:20. Absentees include Darian and Rinsola. Group had discussion about initial project ideas, everyone's backgrounds, interests and available commitment for the project. The group also decided to meet again sometime soon to futher brainstorm any project ideas. Gave group a brief overview of my background, skills and experience. Also mentioned that I am free and will have time to work on the project. Mentioned to the group that I am happy to be in charge on writing up detailed meeting minutes for the group. | 1 Hour | Yes | I suggested to make the project more female related/ catered to women (since we’re in a CFG degree). Mentioned that I could (potentially) provide some help/ knowledge if group decides on making the project healthcare related.
1 | 2023-04-27 | Made a Slack group workspace which contains 2 channels (project info and announcements) and invited members to join the group. Started conversation by asking team to meet someday between the 28/04 - 02/05. | 15 Minutes | Yes | Will need to post first meeting minutes on slack.
1 | 2023-04-28 | Wrote and uploaded a detail meeting minutes for group's 1st meeting. The meeting minutes contains info such as: meeting date, time & location, attendees, apologies, general announcements, Roundtable discussion points, each member's own discussion points (very detailed) = this is for the logbook, actions taken section, to do lists for everyone/ each member (if needed) and the next meeting arrangements (i.e. Date, Location and Time). I've also written and uploaded Meeting 2's agenda which consists of points to discuss + to do for next meeting as well as future points to consider. I've also uploaded the relevant documents/ resources from CFG slack chat (project workshop pdf, homework week 2, lesson 10) to group's own slack. | 1.5 Hours | Yes | The future meeting minutes and agenda would follow the same exact format. Since the meeting minutes is very detailed and contains what each person did + the points they made during the meeting, team members can then copy and paste their sections from meeting minutes to logbook easily. I'm also the person in charge of making polls in general + communicating with Stavros regaridng any project queries + issues within the team.
2 | 2023-05-05 | Contacted Stavros (teaching assistant) regaridng issue with a team member (Darian). Mentioned that I, along with other people in the team has tried contacting Darian but she has never replied. Mentioned to Stavros that we might need his help contacting Darian on behalf of us instead. Also sent message on slack to ask if group would meet sometime the coming weekend to start on the project/ Homework 2. Suggested that the group would need to meet asap to get project started as group is falling behind and have one less member. | 10 Minutes | Yes | Over time, Stavros has confirmed that he didn't manage to get any response from Darian on his end as well. This means that from now on (and last time), Darian is not apart of the team. Also voted on slack to have next meeting on the 7th, 8th or 9th of May.
2 | 2023-05-07 | Group had the 2nd meeting on Zoom at 15:00. Darian was not in the meeting. I've volunteered sending out zoom/ google meets invites for today's and future's meetings.The group had came out with several different project ideas and everyone had in depth discussions about each project ideas. Group also decided to vote on final project idea + prokect management tool using slack polls. Group decided that the next meeting is on Wed 2pm. | 1 Hour | Yes | I've suggested a Plant Care Program and explained that as a person that regularly takes care of plants, I would've loved it if there was a program that tracks watering days, provide info on the type of plants that I have (i.e. amoount of sunlight, water, diseases, etc...). I've also made remarks on other team members' project ideas. Emina's spotify API idea: suggested the project would need to think of more features that makes it different from spotify as they already have their own music reccomendation feature; suggested that the program would need to be more personalised (on top of asking user questions, can also ask them to choose pictures to better understand their current mood and recommend the best songs for them; would need to ask questions that are more in this generation (i.e. using GenZ slang). Rinsola's CFG classroom idea: mentioned (along with RO) that we could sell/ pitch this whole idea as it is but set realistic goals on what programs/ features we want to create (i.e. can say something like, we’re making a CFG students messaging platform [for this group project] as a foundation for a CFG classroom platform future idea). Rebecca's motivation & wellness program: suggested that program could ask users questions to predict their mood and provide the ‘right’/ more appropriate motivational quote (instead of the program just randomly generating one every day). Other remarks: suggested making a slack poll to vote on which project management tool/ platform to use (i.e. Trello or JIRA); Mentioned that I would open a shared Google Docs where everyone could write down more ideas/ features for each project ideas mentioned in this meeting. (This is to help with the decision making for the project idea slack poll before Wednesday).
3 | 2023-05-09 | Wrote and uploaded detailed meeting minutes for group's 2nd meeting. I've also written and uploaded Meeting 3's agenda. I've also created and shared a link to the group's google drive. I've also created and shared a google word document (Name of document: Current Project Ideas, within the shared google drive) which consists of each project ideas discussed (along with points made for each project). I've also created a slack poll which allows for members to vote on which final project idea they would prefer to work on (i.e. NASA API idea, Plant Care Program, Spotify API Idea, CFG Messaging Platform, Motivational & Wellness Program). I've created another slack poll for members to vote on group's project management software (Jira or trello). | 2 Hours | Yes | Final Project slack poll results: Plant Care Program (most votes); Project Management Tool slack poll results: JIRA (most votes).
3 | 2023-05-10 | Messaged Stavros (on behalf of group) to enquire about logbook format (if individual or group based). | 5 Minutes | Yes | Stavros confirmed that each student would need to write their own logbook (so it won't be group based) and that one person would submit everyone's logbook all together.
3 | 2023-05-10 | Wrote more points for the Plant Care Program Section in the Current Project Ideas document. Points made would be included in the logbook's notes section on the right. | 35 Minutes | Yes | Can make it a ‘House Plants’ program instead of just a plant program. Can’t see how farmers (i.e. people that plant crops) would benefit from this, they’d probably benefit more from industry and farming experience/ expertise. So, it’ll just a be a program for people with love for house plants. There might have already been plant programs out there that already have these features collectively. We can make it different from the others by introducing user friendly things such as: making it more personalised by recommending the ‘right’ type of resources depending on the user. The program could either ask the user what type of plant that he/she is owning at the moment (OR they could take a pic and the program would determine which plant it is, though that would involve AI I think). The program would then, save this info and ask more follow up questions (i.e. when did you last watered this plant and what current issues are you having with this plant?) The program could ask it in a drop down multiply choice style way (i.e. choose one of the options). So, program would ask what current issues is your plant facing at the moment? And there’ll be multiple choice style options for the user to choose (i.e. yellowing of leaves, brown burnt looking leaves, see white dots, smells weird, browning of the stem, saw pests on plant, etc….). From there, the program can then ask more questions (i.e. if user picked saw pests on plant, the program will ask: Where are the pests/ what colour or size are the pests? etc….). The program can also asks how free the user is and from there, be able to recommend the type of plants they could own/ should not own. By asking more questions at the start, this way, the program will know more about the user and give the right advice. Maybe the program can help give advice on the user’s existing plants but it could also recommend: what other plants they could buy for next time (based on their habits and interests); plant bloggers/ social medias (i.e. some specialises on certain type of house plants, like monsteras); could recommend the nearest plant shops/ advertise online plant shops for the user; recommend blog/ instagram posts that helps with user’s current plant issues. As a foundation, the program should definitely be able to know what existing plants does the user have. Needs to know their current watering schedule and give some input (i.e. user is watering a certain particular plant too much). Needs to know the current issues of user’s plants and give the reason for the issues (i.e. plant or soil) and give a solution as well. The program should also be able to give the user details of about the plant that their owning (i.e. if user has a monstera, the program should say something like: This type of monstera can tolerate xxxx sunlight, needs to be watered every xxx days, is susceptible to xxx diseases, would need to be fertilised xxx times, needs xxxx type of soil). Would be a great idea for the users to be able to interact with each other. Much like a social media type of thing. Though that might be too challenging for the group. (often times we need to wait for the algorithm to show us the content that we want or we’ll have to search for a specific plant influencer, instagram for example, is too saturated, it has content of everything. What if we make a social media platform for just plant people. They’ll be able to share their plants, message with each other, host events, sell cuttings, exchange cuttings, etc….). My main concern is: we’ll need a really big database?? (Maybe we can use third party services) and if just doing the foundation of the program should already be too complex for the group (they’ll be frontend and backend in this case). For front end, is there an option to just use third party services as well. Would we want the program to be a website or a mobile app? Maybe could think about making the plant program very specific instead. (focusing more on diseases or focusing more on recommending the right type of plant to the user).
3 | 2023-05-10 | Group had the 3rd meeting on Zoom at 14:00 - 15:10. Darian and Ying Ting were not in the meeting. The group decided on: regular meeting time (everyday Wed 2pm); finalised on project idea (Plant Care Program) and had more in depth discussion regarding the program; having another meeting before next Wed (I will create another slack poll to vote for a day/time); distribution for Homework 2 (every member except for Ying Ting, would have a section they're responsible of); Group decided that program would be a website instead of mobile app and that the group doesn't need a scrum master, what I (Jia Chi) is doing now is enough (i.e. making meeting minutes, meeting agendas, google drive, slack polls, follows ups, reminder messages, etc....). After this meeting, I will need to create another slack poll where members can picj the type of the work they would want to responsible of (i.e. frontend, backend, etc...); I would also need to create a new shared google docs for Homework 2 as well as contact Ying Ting separately to give her a recording of meeting + summary of meeting + what she'll need to do moving foward. | 1 Hour 10 Minutes | Yes | I gave a brief overview of own points written in the ‘Current Project Ideas’ shared google document. Highlighted that the program would be ‘House plants’ focused instead of focusing on all plants (i.e. crops/ tomatoes would not be included). Thus, need to find/ research for relevant house plant APIs. I also mentioned that there might be complications with DB(s) as project like this might require a huge DB to store users’ input data + that there are plant programs out there already and highlighted that the group’s program would need to include features that are distinct from other ones in the market. I also prompted the discussion on how we would make it personalised + how we would ask for the user’s input (i.e. would we ask a chains follow up questions? Or ask the user to take a picture and using an AI model, the program will then, identify the plant as well as any obvious issues involved? Or would we do a mixture of both? Also mentioned that the program has potential to include a lot of complicated features (i.e. the program can be made like a plant social-media kind of thing, where the users can interact with each other, exchange cuttings, sell their own cuttings, etc….).
3 | 2023-05-10 | I created a new shared Google docs called 'Homework 2 DRAFT' and pasted the content from the Current Project Ideas shared google doc. I've drafted and section the Homework 2 DRAFT as Homework 2 suggested. I also suggested to the group that each member should colout code what they've written so that we would't interfere with each other's work + easier for logbook input. | 8 Minutes | Yes | N/A
3 | 2023-05-11 | Wrote and uploaded detailed meeting minutes for group's 3rd meeting + Meeting 4's agenda. I've also created 2 slack polls: 1)Next meeting date before regular meeting on Wed (ie. 13/05 or 14/05 or 15/05). 2)Which section each member would be interesed to work on (i.e. frontend, backend, mixture of both, unit tests). I've also messaged Ying Ting personally to send her meeting recordings + reminder to read the meeting minutes + given short summary of meeting points and what she'll need to do next + asking her to inform the group of any comments/ updates afterwards. | 1.5 Hours | Yes | Result for poll 1: 13/05 (most votes); Results for poll 2: (FrontEnd: Rinsola; Backend: Rebecca, Ying Ting, Jia Chi; Mixture of both: Emina; Unit testing: everyone but Ying Ting)
3 | 2023-05-11 | Discussed with Rebecca and suggested that PlantPal would be a good name for group's plant care program. | 1 Minute | Yes | N/A
3 | 2023-05-12 | Opened a new GitHub organization page for group as well as send email invites to everyone. | 3 Minutes | Yes | N/A
3 | 2023-05-12 | Sent a zoom link as me, along with some other team members decided to have an impromptu meeting at 18:20 - 18:41. Attendees include me, Emina and Rinsola. Aim of the meeting was to go through any last minute details of Homework 2. Points discussed include: PlantPal would be a WebApp; submitting Homework 2 before 10pm tonight (everyone would need to finish their own sections and I will proofread and format document properly + submit the final document). Group had finalised some feature points in the web app. | 21 Minutes | Yes | I prompted discussion about how we could make our web app available in all languages (i.e. whether it would be easy to integrate any third party translator program into our web app, like Google Translate). Also prompted discussion about how we would send reminders to our users? Since it’s a WebApp, would we send reminders in the form of emails then? I also emphasize that the backend (especially APIs and DB) is heavily accessed, hence, should be prioritised. Suggested that the group make sure that the backend is done before working on frontend (note: Amy mentioned that frontend is optional). I suggested that extra features (i.e. PlantPal Social Media Feature) could be used as an answer in the presentation (instead of being actually implemented) when markers asks: “How could you make your web app better?”.
3 | 2023-05-12 | Worked on my own sections responsible for Homework 2. I wrote: Project Motivation Section: What does PlantPal do? Why make a plant care program? ¦¦ Current Program Specifications Section: The user prompt is as follows section & PlantPal's Key Features section (AI Plant Identifcation, My Plants, 50% of My Plant Calendar, Plant Helper) ¦¦ References. | 4.5 Hours | Yes | To see my contribution/ look at the specific paragraphs/ points that I've written for Homework 2, please use the final Homework 2 submission + what I've written in the current row for the activity/ task column on the left as reference. I've written 60% of the report and was also in charge of proofreading, formating and submitting it as well.
3 | 2023-05-12 | I've sent follow up/ reminder messages across both channels on slack throughout the day to ensure that the group woud finish their sections on time (before 10pm). | 5 Minutes | Yes | N/A
3 | 2023-05-12 | I've sent the last few follow up messages at 9pm to ask if everyone's done with sections for Homework 2. After confirming that everyone's done, I proofread + reformatted Homework 2 for submission (i.e. making it look presentable and structured). I've created a new GutHub Repository and submitted Homework 2 via Slack (message to Stavros) and mentioned that PR would be created after he accpets my invitation. | 1 Hour 10 Minutes | Yes | Submitted Homework 2 on Slack @ 9:57pm.
3 | 2023-05-13 | Sent a zoom link as me, along with Emina and Rinsola had decided to have an impromptu meeting between 14:15 - 15:00. Aim of the meeting was for us to start having more in dept backend logic discussion regaarding the PlantPal's features. Some group points made: agreed that group should have a full-group meeting soon (so to start distributing coding tasks); me, Emina and Rinsola expressed whcih feature(s) we would each like to work on (i.e. Emina: anything but My Plant Calendar; Rinsola: My Plants + DB; Me: Plant Helper). We also agreed that another full group meeting should be held before regular meeting next wed 2pm. | 45 Minutes | Yes | I started the meeting by laying out the main 5 features of the WebApp that each person could work on (AI Plant Identification, MyPlants, My Plant Calendar, Plant Suggestions, Plant Helper) and suggested that everyone work on one feature each. I also expressed concern for the AI Plant Identification feature. This step would only be easy if there’s a good Plant API and relevant AI model that we could combine. I stressed that making a really good, clear, concise and easily accessible DB is one of the more important tasks as most of everyone features would retrieve the same types of data from the same DB. The group should be able to view and retrieve the required information easily (would make programming more efficient and quicker for everyone). I also admitted that have no experience in APIs and making good DB and would prefer if other members (with greater experience) to work on the initial features instead. Finally, I would want to work on the ‘Plant Helper’ feature as it’s the only one where I can envision (backend wise) and during meeting, has my backend logic for this feature.
3 | 2023-05-14 | Mentioned that from side meeting 2, group should meet again before next wed's regular meeting. I also created a slack poll for members to vote on next meeting date and time (i.e. today 3pm or Monday 2pm/4pm). | 2 Minutes | Yes | Results of Slack poll: Monday (15/05) 4pm (most votes)
4 | 2023-05-15 | Wrote and uploaded detailed meeting minutes for Me, Emina 7 Rinsole's 1st and 2ns side meetings on the 12th & 13th of May, respectively. I've also uploaded the recordings for both side meetings. In addition, I've opened up a new shared google docs, named: PlantPal features: Member Distribution. In this shared document, people can write down any backend logic ideas/ points for each feature. I also suggested that members can add their name beside the feature they're interested to work in. | 2 Hours | Yes | In the PlantPal Features: Member Distribution shared google docs, I've written these points: Create a table in DB which is ordered by date and what happens is your intention you will update the blog page twice a week with videos and articles to share, and you will go to the backend and put in the relevant info in the DB. So, it will be in a date sequence (latest date on top) and each object has its own keys (i.e. title, description, picture URL, content, summary, etc....). What you envision is on the front end and the good thing about these objects is they have consistent values. On the front end, all you need to do is make the HTML and CSS interface once and then you can recycle them. In each front-end interface, there will be a java script logic which will retrieve the information of these objects and will display them in my html tags. For the blog page, if using Python as the back end, can use it as an API endpoint, so Java will be calling that endpoint in Python. In Python, set up an API endpoint which will do something (i.e. retrieving an object from a DB and returning the value). Front-End look: <title> <video pic> <description> Instead of hard coding the content/ URLs, what you will do is, you will variabilise it and with a for loop, javascript can retrieve the objects and paste them in.
4 | 2023-05-15 | Sent Zoom link and group had the 4th meeting on Zoom between 16:00 - 16:50. Darian and Ying Ting were not in the meeting. The group decided on: having more regular meeting days (every: Wed 2pm + Friday 4pm + Thursday CFG group sessions); the latest that anyone should start their own report bits would be on the 25th of May; using Rapid API for PlantPal; distributed tasks accordingly (except for Ying Ting). After this meeting, I would contact Ying Ting separately to give her a summary of meeting + what she'll need to do moving foward. | 50 Minutes | Yes | I started meeeting conversation by giving group a brief overview/ summary of contents discussed from Side Meeting 2. For AI plant identification feature, I suggested that group start looking for free AI models that the project could use. If not, the group would need to resort to asking questions to get user input instead (i.e. the type of plants the user have currently). If the user knows the name of the plant, they could just input it in, if not, there’ll be reference pictures to help them on the side. If it comes down to this, could mention AI plant identification as an improvement/ challenge in the final report/ presentation. I mentioned that I would be happy making UX/UI/ frontend PlantPal mockups for the presentation and final report (to make the whole thing more presentable). I also suggested that the team has internal deadlines (i.e. when to start writing final report, etc…) and highlighted (again) that some members are obviously doing more backend than the others. Whoever that finishes first/ have less to do can write general report bits/ work on presentations/ help other people in their code. Emphasised that I was in charge of the ‘Plant Helper’ feature.
4 | 2023-05-16 | Completed my own PlantPal's Daily Standup for today @1pm. | 1 Minute | Yes | In the daily slack standup today: I mentioned that I'll start coding some functions and submit the latest meeting minutes. Also mentioned that I've started typing up the meeting minutes + wrote some backend logic ideas for my feature.
4 | 2023-05-16 | Started researching on how to write api endpoints for youtube videos + learn how to run a flask app. Wrote a simple short sample endpoint code as well. | 30 Minutes | Yes | Was confused about how I would want to test my code in the future, was thinking that I would actually need to make a really simple html frontend to test my endpoints? But I am aware that this wouldn't give any marks though.
4 | 2023-05-16 | Wrote and uploaded detailed meeting minutes for group's 4th meeting + Meeting 5's agenda. I've also messaged Ying Ting personally to send her: reminder to read the latest meeting minutes + given short summary of meeting points and what she'll need to do next (suggested that she form sub group with Rebecca as she's handling 2 features simultaneously, and could use some help) + asking her to inform the group of any comments/ updates afterwards. | 1 Hour | Yes | N/A
4 | 2023-05-17 | Completed my own PlantPal's Daily Standup for today @ 12:43pm and sent a reminder message to group that there'll be a meeting today @ 2pm. | 4 Minutes | Yes | In the daily slack standup today: I mentioned that I'll write the meeting minutes today, do some PlantPal coding (create table for urls) and complete Homework 3. Also mentioned that I've submitted the meeting minutes 4 + started on a little bit of coding already.
4 | 2023-05-17 | Sent Zoom link and group had the 5th meeting on Google Meets between 14:00 - 14:30. Darian was not in the meeting. The group decided on: everyone working on their own features and giving a follow up on their code in the next meeting; using the rest of the CFG workshop time tomorrow to have a collaborative coding session together. Every member have a brief overview of their coding work so far + mention any coding issues that they might have. Group also had a discussion about how the recovery plan could be implemented. | 30 Minutes | Yes | I asked Emina and Rinsola about soil type and fertilising data (currently, in the main.py file, there aren’t any data on those). and highlighted that fertilising and soil type are quite important elements that should be included in the program. I also suggested that instead of putting the recovery plan into the calendar (i.e. today would need to repot this plant, put this xx chemical to kill xxx pest after xxx days, etc…), the web app could generate a simple side note/ message at the bottom of the calendar, which tells the user: “This plant is currently overwatered and has root rot, please change your plant’s soil and make sure that the soil is a ‘chunky soil type’. When repotting, please make sure to cut out any dirty/ rotten roots with a clean scissor and soak the healthy roots in xxx ration of water to hydroperoxide solution for xxx time.”. This feature could be called ‘My Plant Doctor’ and it could also tell the user to refer to ‘My Plant Friend’ section and ask them to watch a video tutorial on how to repot properly, for example. I mentioned that I might change the name of feature from ‘Plant Helper’ to ‘My Plant Friend’ instead. I also mentioned that I would want to focus on uploading video tutorials (with typed out summary at bottom of vid) instead of blog posts. Showing users how to repot (for example) in video format is easier than telling them how to 9text format). I then mentioned that instead of making a program that automatically scans and uploads video tutorials from YT (i.e. using filters), it would be better for PlantPal’s audience/ cause for group to manually upload video tutorials that were cherry picked. Finally, I also mentioned that I would maybe make a very simple javascript frontend for this feature, so that JL can check if her backend endpoint(s) can be retrieved by a frontend. In a way, it’ll be a form of testing for the code.
4 | 2023-05-18 | Wrote and uploaded detailed meeting minutes for group's 5th meeting + Meeting 6's agenda. I've communicated with Rebecca directly regaridng new ideas/ points I've thought of for the recovery section of PlantPal as well. | 45 Minutes | Yes | My message to Rebecca: what do you think about making the message a small to do list? Something like: Your plant is currently overwatered and has root rot, you'll have to: Step 1-4 (for example) with tick boxes on the side for the user?? then, asking user to refer to videos 1 & 2 on how to repot and identify which root has root rot? (for example) This way, the user would know what to do (visually) cuz we can ask them to refer to vid tutorials instead of us giving step by step pictures or smth? New Message: I was also thinking that the plant would be diagnosed at the plant identification bit? While identifying the plant: I'm not sure if Emina has an AI model in mind (which can identify + diagnose the plant), if not, then we can do plant identification + diagnose through asking the user questions about the plant (using pictures as reference for them). So, after the program has identified the plant, the program could ask the users if their plant might look like they're not doing as well as it should? If yes, then it'll prompt another question (i.e. what immediate problems/ symptoms are you seeing?) The user will then have multiple choice style answers to pick. (i.e. brown leaves, yellow leaves, brown tips, seeing white spots on leaves, red coloured spider like mites on stem, white coloured pests on back of leaves, etc.... --> this is where we'll have to refer to the diseases bit & given them answers to pick from + with reference picks maybe?) So this is how the program will find out if the plant has a problem? (i.e. yellow leaves with foul soil smell = overwatering and root rot) or (i.e. white web like clumps on back of leaves = mealy bug infestation) and this info would then also show up in the My Plants feature, so that the plant user remember this particular plant has an issue. For the recovery plan, can ask users to look at the 'My Plant Doctor' message section in 'My Plant Calendar'? New Message: I think u're right, we might just end up using lots of if statements lol, we'll see. I think if it's just overwatering, we'll push the watering days to a week/ a month (depending on the season) but it'll be a different case if there's root rot as well. For root rot, there's no treatment, you just need to trim out the bad roots, soak the remaining in a chemical solution and change your soil + water the new soil (these need to be done asap). treatments are really only for pest infestations and they should be done asap. So we don't need to tell them when to add the treatment? We just need to tell them to do it asap.
4 | 2023-05-18 | I didn't get to do much coding today but I've tried running the flask app (which consists of a very simple trial and test endpoint code) and it failed, would need to figure that out. I've started writing mysql code on creating tables (I've yet to finalised on what exactly would I want to include in my feature, for example, would I only include videos by date or make it more complicated?), so I've yet to insert any data in the mysql tables. | 24 Minutes | Yes | N/A
4 | 2023-05-18 | Completed my own PlantPal's Daily Standup for today @ 6:40pm. | 2 Minutes | Yes | In the daily slack standup today: I''ve mentioned that I'll continue my plant friend coding. Also mentioned that I've submitted meeting minutes 5 + need to work on Homework 3.
4 | 2023-05-19 | Completed my own PlantPal's Daily Standup for today @ 2:31pm. | 2 Minutes | Yes | In the daily slack standup today: I've mentioned that I'll continue working on my backend endpoint code for My Plant Friend + send a webframe mockup to Rinsola. Also mentioned that I've only worked on Homework 3 yesterday.
4 | 2023-05-19 | Had a conversation with Rinsola as she reached out to ask for my update + to discuss about making a frontend. She mentioned that she and Emina has decided to work on frontend despite the group's decision (but hasn't told the rest of the group about this yet). While confused, I needed time to think about this but have also mentioned that I send her a ui mock web frame diagram on how I wanted my feature (My Plant Friend) web page to look like. | 12 Minutes | Yes | N/A
4 | 2023-05-20 | I've made and sent Rinsola a ui mockup web frame diagram on how I wanted the My Plant Friend web page to look like. Here's the link to view it: https://app.uizard.io/p/0261f4b5 (please press the add notes section (at the bottom right) to see my step by step notes which explains each of the web page sections). | 46 minutes | Yes | N/A
4 | 2023-05-21 | I've sent a message to Rinsola regarding my thoughts/ issue on making a frontend. | 2 Minutes | Yes | Message: I do want to emphasize that while making a frontend is good, Amy specifically mentioned that doing one doesn't necessarily give any marks at all. I personally think that maybe just making a frontend home page/ mockup is good enough (instead of making a frontend for the whole thing just cuz we don't have a lot of time left at all). So, it'll be good for the whole team to have a discussion and have an official decision on this?
4 | 2023-05-21 | Team has been pushing Friday's meeting date till now (group still hadn't managed to have a catch up meeting). I've prompted and reminded the group that we should meet on Monday latest to see every member's progress @ 11:26 pm. | 5 Minutes | Yes | Everyone eventually agreed on having a meeting tomorrow @ 2pm.
4 | 2023-05-21 | Since making the webframe, I've had a clearer idea on how I want my feature to look like. So, I've compiled a list of 22 youtube videos (topics, title, description, video_url) and have used these data and inserted them into my tables in MySQL. I've also made more endpoints (i.e. endpoint for getting the current week's feature videos + endpoint for getting videos sorted by date DESC + endpoint for get all the different houseplant topics, such as repotting, watering, pest care, etc...). | 1 hour 39 minutes | Yes | Know that I know more about how my feature looks like, when I have more time, I'll continue the mysql code for the tables + create the rest of the other endpoints. The current endpoints that I've create aims to fetch the current feature week's videos' data; fetching all videos and sorting them (newest to oldest); fetcning all topic names. These are done by GET requests, which connects to MySQL and execute a particular query and retrieves the relevant data.The data fetched would be stored in a list and converted into JSON format.
5 | 2023-05-22 | Completed my own PlantPal's Daily Standup for today @ 10:11am. | 2 Minutes | Yes | In the daily slack standup today: I've mentioned that I would need to fix some issues in my backend endpoint code + write up the meeting minutes for today. Also mentioned that I've just only been working on making endpoints for my plant friend.
5 | 2023-05-22 | Needed some clarification on the frontend issue, so I had a slack chat conversation with Emina as well (as Rinsola mentioned both her and Emina decided to work on frontned out of the blue without notifying the team). | 10 Minutes | Yes | Basically mentioned that she didn't necessarily agreed to it after knowing that the frontend would be in React format but she also very agreed on not making a frontend as that would require more time, effort and collaboration between team members (which everyone don't have) + it doesn't give any marks. We also communicated on how best to relay this not-making-any-frontend-suggestions to Rinsola (as we are aware of how much she wants to do it).
5 | 2023-05-22 | Sent Zoom link and group had the first half of the 6th meeting on Google Meets between 14:00 - 14:34 (attendees include: me, Emina and Rebecca) and the 2nd half of the 6th meeting on Google Meets as well, between 14:50 - 15:15 (attendees include me, Emina and Rinsole). Group decided on not making a frontend + not connecting frontend to backend. Internal deadlines were decided: Everyone finish 50% of their own code by Wed 2pm and finish 100% of their code by Friday’s meeting (where everyone would be in a meeting together to combine everyone’s code). Everyone should try making sure that their own code hits the must have criteria + implement as much good to haves as possible. Also agreed on the approach that: as long as the final code hits the necessary criteria(s) collectively, it’ll be good enough. Reminder that logbook is done individually but submitted by one person (it’s how the markers know what you’ve done and give you marks). Reminder: Final report, Code & Logbook submission on the 28th of May. Every member also gave brief overview of their coding work so far + prompt discussion on any issues that they might have/ improvements that could be implemented. | 59 Minutes | Yes | I've Prompt discussion on whether a frontend should be implemented or not + whether group should connect frontend to backend? (This is because RO expressed interest in making a frontend as well as connecting over the weekends). For this, I had mentioned that I've asked Stavros (teaching assistant) whether any marks would be given for making and connecting a frontend, and the answer was: No marks given at all. Hence, I’ve suggested against the idea of making and connecting a frontend as this would mean more collaboration and I am also aware that some other teammates might not feel comfortable creating endpoints as well (as they don’t know how to). I've told RO that she is free to do any frontend but the group would not connect our backend to her frontend as no one knows how to do + doesn't ahve the time to learn so. After RO had shared the project criteria (must have + good to have): I’ve also mentioned that the group should definitely hit all the must haves and the good to haves can be optional. People in charge of their own features can decide which good to have(s) to implement, 3/5 ish good to haves per feature would be good enough. I also asked details regarding plant identification (i.e. if there’ll be an AI involved) and if EE would be comfortable adding another set of questions (asking users if plant 1 has any diseases for example) for her feature (for when program is gathering user inputs). I also mentioned to both EE and RH that if they needed any help on the diseases and treatment bit, I'll happy to help. I have a brief overview of parts of my code that I've done (screen shared with RO too) as well as mentioned what I’ll do next. I'm also in charge of giving a list of treatment plans (to do lists) for RH (for her treatment section in her ‘My Plant Calendar’ feature) after this meeting. I've also suggested that the group could have a code checkpoint on Wednesday which shows that everyone has completed at least 50% of their own code. Ultimately, to make everyone happy, I've mentioned that the everyone should try making sure that their own code hits the must have criteria + implement as much good to haves as possible. Also agreed on the approach that as long as the final code (everyone’s code combined together) hits the necessary criteria(s), it’s good enough. Also mentioned that Stavros confirmed group could reuse bits in Homework 2 for report (it wouldn’t count as plagiarism).
5 | 2023-05-23 | Wrote and uploaded detailed meeting minutes for group's 6th meeting + Meeting 7's agenda. I've also reuploaded the submision and project criteria images (must haves + good to haves) shared by Rinsola, so that the group could use them as references. | 1 Hour 13 Minutes | Yes | N/A
5 | 2023-05-23 | I've made all the necessary endpoints for my feature. The rest of the endpoints are as follow: endpoint for getting videos by topic; endpoint for getting ads (recommendation by Rinsola); endpoint for allowing user to rate and comment on each video (POST Request); endpoint for getting the rating and comment for a video. I've also started writing unittests for the endpoints. I've finished forming MySQL tables as well and ran all my endpoints. Through some errors and small changes in the code (mainly synthax errors), I've successfully ran all my endpoints and got the right output in my browser/ Postman when I've placed and ran the urls. | ~4.5 Hours | Yes | Had a small hickup while writing the endpoint where the users can rate and comment on a particular video (post request), there were just synthax errors, it was solved but took too much uneccessary time. Need to think about what kind of unittests am I going to write (i.e. write one which checks the HTTP response or write on which checks the output in the browser). The rest of the endpoints (GET requests one which fetches data, follows more or less the same format as the endpoints made earlier (21/05/2023), except for the POST request endpoint. I know that the endpoints ran and worked successful as I've manually tested these endpoints by running the flask app, looking at the status codes (i.e. 200 for success) and manually checking every URL and making sure that the right videos were fetched and presented in a list in JSON format. For the user rate and comment endpoint, I've checked that the MySQL table updates itself after a rating and comment is submitted.
5 | 2023-05-24 | Sent Reminder to Group that there'll be meeting today @ 2pm and that everyone should be 50% done with their onw code bits. | < 1Minute | Yes | N/A
5 | 2023-05-24 | Completed my own PlantPal's Daily Standup for today @ 10:12am. | 2 Minutes | Yes | In the daily slack standup today: I've mentioned that I would need to look more into Postman + api endpoint authentication + write up the meeting minutes for today. Also mentioned that I've made all the necessary endpoints + started on some unittests writing since Monday.
5 | 2023-05-24 | I've tested all endpoints (not just the post request one) on Postman and all of them ran suucessfully. I've also looked into including authentication for my feature and found out how complicating that would be + my feature should be open for everyone (non members should be able to look at video tutorials as well). I've also started writing exception classes for some of the endpoints as well as the relevant unittest. I've added custom messages in my backend code as well (these messages would get printed out when the system has ran successfuly/ when there's an specific error). | 1 Hour 43 Minutes | Yes | Have finsihed most of everything, would just need to write the rest of the exception classes + unittests as well as running all unittests.
5 | 2023-05-24 | Sent Zoom link and group had the 7th meeting on Google meets between 14:00 - 14:37 (attendees include me, Emina and Rebecca). Announcements include: "Thursday meeting: this would be a small code checkpoint meeting where group can hash out at last mins issues before Friday’s final code meeting." ; "Friday’s meeting: Everyone finish 100% of their own code before meeting." ; "Everyone should try making sure that their own code hits the must have criteria + implement as much good to haves as possible." ; "Also agreed on the approach that: as long as the final code hits the necessary criteria(s) collectively, it’ll be good enough.". Every member gave brief overview of their coding work so far + prompt discussion on any issues that they might have/ improvements that could be implemented. Group dad discussion about OOP principles where everyone would need to think of places/ new ideas where OOP principles can be implemented (i.e. classes). At least one person’s code would need to include the use of OOP principles. Group also agreed that soil type would need to be taken out of the program as Rapid API doesn’t have any info on it. Group agreed that PlantPal would be UK based (we don’t have enough plant info to make it international at the moment). Looking at the Final Report Mark Scheme under the Links & Resources bookmark on Slack: group started looking into the report deliverables and section distributions and decided that: 1 to 2 people would be in charge of each section: Introduction, Background and Conclusion. Everyone would write their own bits for: Specification & Design, Implementation & Execution and Testing & Evaluation. | 37 Minutes | Yes | I gave a brief overview of My Plant Friend’s current progress: I mentioned that I've written the necessary endpoints, some unittests, MySQL tables as well as started a little bit on the exception classes and error code. I've also highlighted that I will focus on testing from now on (either unittests or using Postman or use both). I've asked Revecca on how the program would know when the user has last watered a particular plant? (Which feature would this question be asked at? Plant identification or Plant Calendar?). I also relayed replies sent from Stavros: Presentation is 15 minutes long + everyone would need to present at least a slide/ section; Final report is Group based; The deadline for logbook(s), final report and code is at 11:59pm on Sunday, May 28th. I mentioned that for fertilising, instead of using APIs, suggested that RH can manually set fertilising frequencies instead (based on seasons): Winter: once every 2.5 months ¦¦ Autumn: once every 1.5 months ¦¦ Spring: once every 2 weeks ¦¦ Summer: once every week. For watering in Plant Calendar feature: suggested incorporating seasons in simple way: Winter: once every 1.5 months; Autumn: once every month; Spring: once every 2 weeks; Summer: once every week. My remarks on final report distribution: Would like to work on Background section (as JL written most of it in Homework 2) + will welcome anyone else to work on this section as well.
5 | 2023-05-24 | I've opened up a new slack poll for when (i.e. 6pm or 2pm) would the group want to meet on Friday to combine everyone's code together. | 2 Minutes | Yes | Results of Slack poll: Friday (26/05) 6pm (most votes)
5 | 2023-05-24 | Wrote and uploaded detailed meeting minutes for group's 7th meeting + Meeting 8's agenda. I've also reminded the group to think of ways to incorporate OOP principles (i.e classes) in anywhere of our code. | 1 Hour | Yes | N/A
5 | 2023-05-24 | Wrote the rest of the exception classes and unittests for the rest of my features. | ~1.5 Hours |  | I didn't write an exception class and unittests for the get_all_videos() endpoint as there were too many youtube URLs to be manually inputted.
5 | 2023-05-24 | Wrote a word document for Rebecca, named: houseplant treatments, which contains detailed treatment plans (In the form of to do lists) for different plan conditions (i.e. diseases/ pests infestations). The document has 10 different houseplant conditions (top 10 in uk) + their respective treatment steps. I've include very detailed treatment plans (through research + own experience) for conditions like: overwatering/ root rot; underwatering; yellowing leaves; leaf spot/ fungal diseases; leggy growth; fungus knats infestations; thrips infestations; spider mites infestations; mealybugs infestations; aphids infestations). | 1.5 Hours | Yes | An example: 1) Overwatering/Root Rot/ yellowing leaves/ wilting: • Take houseplant off the soil to do quick check-up on roots + throw away this oil (as root rot is contagious). • Using a clean pair of scissors, cut off the roots with root rot (they would look rotten, brown/ black, and slimy), only leaving the white healthy roots behind. • Take a bowl and fill it with mix of 2 parts water and 1 part hydrogen peroxide. • Soak the healthy roots in bowl containing the mixed solution for 30 minutes. • Using a new pot, fill it up with new healthy well-draining soil (make sure to use the right soil type for your plant) and proceed to repot your plant. After repotting, please lightly water your plant. To learn how to repot, you can head onto My Plant Friend to watch video tutorials on repotting. • In the future, please reduce watering frequency by adhering to your watering schedule and allow the soil to dry out between waterings (one way to test: take a wooden stick, push it right to the bottom of the pot and take it out. If the stick is dry, it’s time to water). To learn more about how and when to water your plants, please head onto My Plant Friend for video tutorials.
5 | 2023-05-25 | Sent Rebecca the houseplant treatments word document which include very detailed treatments plans (in the form of to do lists) for different plant conditions (i.e. diseases/ pests infestations) @ 12:24am | <1 Minute | Yes | N/A
5 | 2023-05-26 | Completed my own PlantPal's Daily Standup for today @ 10:56am + send the group a reminder on slack that everyone would need to finish 100% of their own code bits by 6pm today. | 2 Minutes | Yes | In the daily slack standup today: I've mentioned that I would work on running my exception classes + unittests today. Also mentioned that I've done everything that I need to do (apart from running some of my exception classes + unittest) since Wednesday.
5 | 2023-05-26 | Ran my backend code + tests and made sure that all of the unit tests and manual tests passed through as intended + make last minute changes and checks. | 3 Hours | Yes | To be fair, there wasn't much error while running the code, just synthax errors here and there, so it shouldn't have taken this long. The main error was importing my flask app into the test file: It didn't import it no matter what, I spent hours trying to find out why/ changing code here there, to only find out that: I only needed to change my filename (containing the flask app) to app.py for it to work. #coding
5 | 2023-05-26 | Sent Rinsola via private slack chat: My sql code for making the tables for my feature. | < 1 Minute | Yes | N/A
5 | 2023-05-26 | Sent Zoom link and group had the 8th meeting on Google Meets and Zoom between 18:00 - 20:39 (attendees include: everyone but Darian). I've recorded the meeting for Ying Ting as she needed the a recording of us running our files as she volunteered to be the one combining all our files together and making sure that everything works as one. Everyone started by doing some finsihing touches to their code, then, one by one, we all made pull requests to push our own codes. For the rest of the session, the group mainly discussed points on: merging everyone's code together, sql connection, endpoints, flask app(s), tests, project/ file structure, how to structure our code, etc. Instead of combining the code on the spot, Ying Ting has volunteered to work om combining them herself bby Saturday evening. Here are the work distributions and announcements for the future: YL: In charge of combining everyone’s code together + write her own sections of the report (plant suggestions + final code collation) + requirement.txt file. RO: In charge of refractoring everyone’s code everyone uses the same sql connection function + write her own sections of report (My plants db, user log in) + write conclusion in report + write README file. RH: In charge of: Trying to make endpoints + write her own sections of the report (My Plant Calendar) + combining everyone’s logbook(s). EE: In charge of => writing her own sections of the report (Plant identification, My plants functions) + write introduction in report. JL: In charge of => opening new google docs for final report/ making final report outlines + writing her own sections of the report (My Plant Helper) + write background/ intro in report + format & submit final report. • Deadline for logbooks: Sunday 6pm => SEND TO REBECCA • Deadline for report: Sunday 8pm => SEND TO JOANNE • Deadline for Final Code + DB+ README + requirement.txt: Sunday 9pm | 2 Hours 39 minutes | Yes | I've not written a detailed meeting minutes for this time (the meeting was just too long), so I don't remember the exact points that I made during this meeting. What I do know is that I started the meeting as usual ( start by making sure that everyone is done with their bit). After everyone has made their pull requests, I've then prompted the conversation on how we should combine the code. Like I mentioned in the activity task column on the left, the group had several discussions regarding things like: merging everyone's code together, sql connection, endpoints, flask app(s), tests, project/ file structure, how to structure our code, whether we'll put all our test files into a separate folder, etc. Me and Ying Ting were leading the meeting together (talking/ making points most of the time) whilst the other chimed in occasioanlly when they'd want to make a point. I've also prompted discussions on deliverables and deadlines (internal and official) as well as making sure everyone knows what to do next/ is comfortable with what they'll do next. I've recorded the meetings as well, so that I could send them to Ying Ting later on.
5 | 2023-05-27 | Wrote and uploaded a less detailed meeting minutes for group's 8th meeting (which consists of just reminders of what each person would need to do oving forward). I've also opened and formatted/ outline a new shared google doc, named: Final Report Draft. I've also sent this message to the group saying: "As I was formatting the file, I saw that there were quite lot of bits that should be written by only 1 person (I've outlined throughout the file which bits are for everyone to write + which bits are not). I'm suggesting that we all add our names (i.e. JL) beside the bits that you would want to work on (like I've done so in the doc). Please do so by tomorrow afternoon 1pm! I'll give a final report distribution update on Slack after (just so everyone's clear~)". | 1 Hour 16 Minutes | Yes | N/A
5 | 2023-05-27 | Wrote 80% of my own report bits + communicated with the rest of the team on any updates and changes. Sent a reminder to the group as well on internal deadlines for report, logbooks(s) and README file. | 4 Hours | Yes | The sections that I'm in charge of for the report: Background, Team Member Roles, Project Changes, Appendix,, References; The sections that I've contributed to: Technical & Non-Technical Requirements for My Plant Friend, Tools and Libraries, Achievements, Challenges, Testing Stategy for My Plant Friend.
5 | 2023-05-28 | Spent most of the day (starting from 12pm till 8:10pm), excluding occasional rest time, lunch and dinner time to work on the report + have detailed report discussions on slack. Once everyone's done finalising their bits/ are happy, I proofread, editted and formatted the final report, to make sure the whole report is perfect. | ~6 Hours | Yes | Though I've written most parts yesterday, everyone had to make big changes all all throughout the report again after having more in depth discussions with the group on slack. Apart from rewriting/ making changes, I also had to made sure that everyone's section is progressing as intended (prompting further more discussions in the chat, communicating with other team members privately on particular stuff, made sure that everyone's happy and writing in a consistent format, etc).
5 | 2023-05-28 | Submitted the Final report + Postman file via GitHub! | 1 Minute | Yes | N/A
Total time:
~ 75 hours and 5 Minutes
Future: everyone would work on their own bits for the final presentation. I will set up another meeting + open up and outline a shared ppt slide on google drive.